## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 79 | 1 |  |  |  | 21 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0
| 10/03 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Wed | Fri | Sun | Wed | Fri | Sun | Wed | Fri | Sun | Wed | Wed | Wed | Wed | Wed | Wed | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2016-09-14 | 9/16 | 9/18 | 9/21 | 9/23 | 9/25 | 9/28 | 9/30 | 10/02 | 10/05 | 10/05 | 10/05 | 10/05 | 10/05 | 10/05 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
5 |  | ——Preparation—— | [23 empty] | Assigned
6 | 1 | Play / study original zelda game | BB | SS | 2 | 0 | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Google search "zelda nes online" and you should figure out how to easily play the game. Otherwise, visit the videogame archive in the basement of the Duderstadt. | Active
7 | 1 | Watch zelda tutorial (canvas) | BB | SS | 2 | 0 | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | There are two Zelda tutorials available for viewing. Read how they're different in the Piazza template repo. | Verify?
8 | 2 | Mess With 494 Quest (Piazza Bonus Template) | SS | BB | 2 | 0 | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 494 Quest was built for you to examine, pilfer, and learn from. | Fixed
9 | [25 empty] | Deferred
10 | [25 empty] | Fact of Life
11 | [25 empty] | Can't Repro
12
13
14
15 |  | ——Player Character——
16 | 1 | Grid-based movement | BB | SS | 4 | 0 | 6 |  | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 1 | Health and damage cooldown (damage-invincibility) | BB |  | 2 | 0 | 3 |  | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A nasty side-effect of not implementing a damage cooldown or "vulnerability-period" is that players die exceedingly quickly.
18 | 1 | HUD and Item Selection Capability (item menu). | BB |  | 3 | 0 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Building menus and simple inventory management systems is necessary in many games, and good experience to get. Be thankful you're not making Pokemon, like the F15 class did.
19 | 1 | Collectable Pickup Capability (Hearts, rupees, items) | BB |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 1 | Bow Weapon Functionality | BB |  | 3 | 0 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 1 | Boomerang Weapon Functionality | BB | SS | 3 | 0 | 4 |  | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The boomerang has many functionalities-- be sure to implement them all!
22 | 2 | Shield - Reflect projectiles. | BB |  | 2 | 0 | 1 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 1 | Bomb Weapon Functionality | BB |  | 2 | 0 | 3 |  | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 1 | Shooting sword at full health | SS |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 3 | Player Death | BB |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26
27
28
29
30
31
32
33
34
35 |  | ——Enemies——
36 | 1 | Stalfos - Skeleton Enemies | SS |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 1 | Keese - Bat Enemies | SS |  | 2 | 0 | 3 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 1 | Goriya - Boomerang Enemies | SS |  | 3 | 0 | 2 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 2 | Bladetrap - Spike Obstacle Enemies | SS |  | 2 | 0 | 1 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 1 | Gel - Slow Enemies | SS |  | 2 | 0 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 2 | Wallmaster - Creepy Hand Enemies | SS |  | 2 | 0 | 4 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The wallmaster reset's Link's position in the dungeon, but not the dungeon itself! Don't be lazy and just call Application.LoadLevel()!
42 | 1 | Aquamentus - Dragon Boss | SS |  | 2 | 0 | 1 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 3 | Enemy Death animation | SS |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Give enemies a chance to drop loot
44
45
46
47
48
49
50 |  | ——Environment——
51 | 1 | Room Transitions | SS |  | 3 | 0 | 3 |  | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 1 | Locked Doors | SS |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 1 | Pushable Blocks | SS |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 2 | Old-Man Room (Simple Speech Engine) | BB |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Speech and dialogue engines appear in many games, often as the primary driver of plot and character development. Zelda's dialogue system is simple, and provides an opportunity for experience.
55 | 2 | 2D Room (Bow Room) | SS |  | 2 | 0 | 3 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 1 | Water tiles (allow projectiles but not physical entities) | SS |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 1 | Populate Rooms with Enemies | SS |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 2 | Make keys show up in rooms | SS |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 5 | Bombs should blow up walls in correct spots | SS |  | 2 | 1 | 1 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | I'm not 100% we're required to do this, lowering priority
60 | 2 | Introduce audio assets | SS |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61
62
63
64 |  | ——Custom Level——
65 | 1 | Design map | BB |  | 4 | 0 | 6 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 1 | Add Lanterns | BB |  | 2 | 0 | 3 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 2 | Add torch item | BB |  | 2 | 0 | 4 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 1 | Add text to explain torch on pickup | BB |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 1 | Populate Rooms with Enemies | BB |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 | 1 | Link knockback sometimes goes into walls | SS |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | "fixed" by disabling link knockback | Fixed
108 | 1 | Player movement animations need fixing | SS |  | 1 | 0 | 2 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | this is awfully hacky but I think it works | Fixed
109 | 2 | Bombs sometimes look uncentered on tiles | SS |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
110 | 1 | Knockback on enemies only goes left? | SS |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
111 | [25 empty] | Reported
112 | [25 empty] | Reported
113 | [25 empty] | Reported
114 | [25 empty] | Reported
115 | [25 empty] | Reported
116 | [25 empty] | Reported
117 | [25 empty] | Reported
118 | [25 empty] | Reported
119 | [25 empty] | Reported
120 | [25 empty] | Reported
121 | [25 empty] | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
144 | [25 empty] | Reported
145 | [25 empty] | Reported
146 | [25 empty] | Reported
147 | [25 empty] | Reported
148 | [25 empty] | Reported
149 | [25 empty] | Reported
150 | [25 empty] | Reported
151 | [25 empty] | Reported
152 | [25 empty] | Reported
153 | [25 empty] | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 21 | 21 | 19 | 17 | 14 | 12 | 10 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0
211 |  | Optimum | [5 empty] | Line | 79 | 79 | 71.5 | 64.0 | 52.7 | 45.1 | 37.6 | 26.3 | 18.8 | 11.3 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0
212
213 |  | Sum | [6 empty] | 73 | 73 | 73 | 73 | 73 | 73 | 73 | 73 | 73 | 73 | 0 | 0 | 0 | 0 | 0 | 0
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 56 | 52 | 52 | 47 | 44 | 40 | 34 | 31 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 |  |  | 2 | [5 empty] | 19 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0
217 |  |  | 3 | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
218 |  |  | 4 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Shane Schulte | SS |  |  |  |  | SS | 41 | 39 | 39 | 37 | 34 | 34 | 33 | 32 | 18 | 1 | 1 | 1 | 1 | 1 | 1 | 1
223 |  | Ben Brenner | BB |  |  |  |  | BB | 38 | 34 | 34 | 31 | 31 | 27 | 22 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
225 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
226 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 79 | 0 | 0 | 0 | 0 | 0 | 0
236

## Daily Scrum
Producer | 10/03 |  | Team Members
Approved | Dates |  | Shane Schulte | Ben Brenner
| 9/14 | Wed | Done: Talked about level design Next: Can't work tomorrow Help: Nothing now | Done: Planned X Next: Implement X Help: —
| 9/16 | Fri | Done: Nothing Next: Work on room transitions Help: N/A | Done: Went through tutorial Next: Can't work Saturday, will start work on grid system Sunday Help: Might need help with basic concepts of grid system
| 9/18 | Sun | Done: Fixed background tile issues, tried to fix grid system, started working on room transitions Next: Implement some enemies Help: N/A | Done: Got the basics of Grid based movement, still needs some polish. Also implemented picking up rupees and hearts. Next: Finish up Grid based movement, start working on Links weapons. Help: Just need some opinions on the movement
| 9/21 | Wed | Finished room transitions, added stalfos enemy | Done: Link turns red and is invincible after getting hit Next: Make sure link jumps back when hit, start weapons Help: —
| 9/23 | Fri | Didn't work | Done: Link jumps back when hit (Its a bit crude, its more like he teleports), started bombs Next: finish bombs, bow Help: —
| 9/25 | Sun | Revised knockback, enemy movement, added door unlocking, hitting enemies | Added the item select menu, game pauses for that when rightshift is pressed
| 9/28 | Wed | Abstracted away Enemy class, added in Keese, populated some rooms with enemies TODO: More enemies, look into knockback issues | Done: Implemented Boomerang, Started bow Next: finish bow, start custom level Help: —
| 9/30 | Fri | Implemented bladetraps, general bug fixes, implemented and placed Goriya enemies | Done: Finished Bow, Edited text file to implement custom map Next: Start torch and lanterns for custom level Help: —
| 10/02 | Sun | pretty much everything
| 10/05 | Wed
| 10/05 | Wed
| 10/05 | Wed
| 10/05 | Wed
| 10/05 | Wed
| 10/05 | Wed